## Infomation
SWP391 - Group 1
I. Members |  |  | II. Project's information
# | Full name | Student ID | # | Field | Value
1 | Phan Thành Hưng | CE180265 | 1 | Project Name | PawHouse
2 | Trần Hữu Tín | CE180262 | 2 | Repository | GitHub
3 | Nguyễn Huỳnh Chấn Hưng | CE180150 | 3 | RDS Document | RDS
4 | Trương Phú Hưng | CE180618 | 4 | SDS Document
5 | Huỳnh Hoàng Huy | CE181847 | 5 | Issues Report
6 | Võ Chánh Huy | CE181002 | 6 | Final Release Document

## Project
THE APPLICATION DEVELOPMENT PROJECT TOPIC PRODUCT BACKLOG
# | Title | Description | Screen / Function | Feature | Iteration | Actor | Assignee | Status | Priority | SRS | SDS | Note
1 | Setup project | Setup idea and member for project |  |  | Iteration 1 |  | Phan Thành Hưng | Done | 1
2 | Write all model classes | Write all model to store database from database |  |  | Iteration 1 |  | Trần Hữu Tín | Done | 1
3 | Write all DAO classes | Write all DAO classes to access data from database |  |  | Iteration 1 |  | Nguyễn Huỳnh Chấn Hưng | Done | 1
4 | Write base for SRS Document | Write base form for SRS Document |  |  | Iteration 1 |  | Huỳnh Hoàng Huy | Done | 1
5 | Design UI | Design UI |  |  | Iteration 2 |  | Trần Hữu Tín | In progress | 1
6 | Implement PawHouse for repository | Write PawHousefile and pawhouse-compose.yml |  |  | Iteration 2 |  | Trần Hữu Tín | In progress | 1
7 | Write code base UI | Write code base UI for project |  |  | Iteration 2 |  | Phan Thành Hưng | In progress | 1
8 | Write nav, sidenav, footer jsp | Write common jsp for reuse |  |  | Iteration 2 |  | Phan Thành Hưng | In progress | 1
9 | Write APIs for dashboard | Write APIs for dashboard | Dashboard | Others | Iteration 2 | Guest, Customer, Admin, Staff, Doctor | Huỳnh Hoàng Huy | In progress | 1
10 | Implment dashboard with charts | Implment dashboard with charts | Dashboard | Others | Iteration 2 | Guest, Customer, Admin, Staff, Doctor | Huỳnh Hoàng Huy | In progress | 2
11 | Implement Authentication and Profile Management Backend | Develop APIs for: Login (UC-E-7-2), Register (UC-E-7-1), Forget Password, Logout (UC-E-7-3), View Profile, Update Profile, Change Password | Login | Others | Iteration 2 | Guest, Customer, Admin, Staff, Doctor | Trương Phú Hưng | In progress | 1
12 | Implement Authentication and Profile Management Frontend | Build interfaces for: Login, Register, Forget Password, Profile View, Profile Update | Login | Others | Iteration 2 | Guest, Customer, Admin, Staff, Doctor | Trương Phú Hưng | In progress | 1
13 | Implement Product Management Backend | Develop APIs for: View Product (UC-E-3-1), Create New Product (UC-E-3-2), Edit Product (UC-E-3-4), Delete Product | Manage Product | Product Management | Iteration 2 | Staff, Admin, Doctor | Nguyễn Huỳnh Chấn Hưng | In progress | 1
14 | Implement Product Management Frontend | Build product display pages, Create product management interfaces (add, edit, delete) | Manage Product | Product Management | Iteration 2 | Staff, Admin, Doctor | Võ Chánh Huy | In progress | 1
15 | Implement Shopping Cart and Payment Backend | Develop APIs for: Edit Product in Cart, View Cart, Delete Product in Cart, Make Payment by Cash, Make Payment by Card | Manage Product | Product Management | Iteration 2 | Customer | Võ Chánh Huy | In progress | 1
16 | Implement Shopping Cart and Payment Frontend | Build product display pages, create shopping cart and payment pages | Dashboard | Others | Iteration 2 | Customer | Phan Thành Hưng | In progress | 1
17 | Implement Service Management Backend | Develop APIs for: View All Services (UC-E-4-1), Add New Service (UC-E-4-2), View Service Details (UC-E-4-3), Update Service (UC-E-4-4), Booking Service Appointment (UC-E-4-5), View Appointment Details (UC-E-4-6), Update Appointment (UC-E-4-7), Cancel Appointment (UC-E-4-8) | Manage Services | Service Management | Iteration 2 | Staff, Admin, Doctor, Customer | Huỳnh Hoàng Huy | In progress | 2
18 | Implement Service Management Frontend | Build service listing and detail pages, Create appointment management interfaces | Manage Services | Service Management | Iteration 2 | Staff, Admin, Doctor, Customer | Huỳnh Hoàng Huy | In progress | 2
19 | Implement Pet and Health Management Backend | Develop APIs for: View Pet List (UC-E-2-1), Create New Pet (UC-E-2-2), Edit Pet (UC-E-2-4), Delete Pet, Health Tracking, Drug Management, Disease Management, Disease Update | Manage Pet | Pet Management | Iteration 2 | Staff, Admin, Doctor, Customer | Trần Hữu Tín | In progress | 2
20 | Implement Pet and Health Management Frontend | Build interfaces for: Pet management, Health tracking and disease management | Dashboard | Others | Iteration 2 | Doctor, Customer | Trần Hữu Tín | In progress | 2
21 | Implement Staff and Doctor Management Backend | Develop APIs for: View Doctor List, Manage Doctor, Create New Account, Edit Account, Delete Account, View Staff Logs | Admin Dashboard | Customer Management | Iteration 2 | Admin | Trần Hữu Tín | In progress | 2
22 | Implement Staff and Doctor Management Frontend | Build interfaces for staff and doctor management | Manage Services | Service Management | Iteration 2 | Staff, Admin | Phan Thành Hưng | In progress | 2
23 | Implement Reporting and Insights Backend | Develop APIs for: View Service History; View Order Products; View Reports by Day, Month, and Year | Dashboard | Others | Iteration 2 | Staff, Doctor, Customer | Phan Thành Hưng | In progress | 3
24 | Implement Reporting and Insights Frontend | Create report and transaction history interfaces | Dashboard | Others | Iteration 2 | Staff, Doctor, Customer | Trương Phú Hưng | In progress | 3
25 | Implement Video Tutorials and Product Comments Backend | Develop APIs for: View Product Comments (UC-E-6-1), Add Comment (UC-E-6-1), Update Comment (UC-E-6-3), Delete Comment (UC-E-6-2), View Video Tutorials | Dashboard | Others | Iteration 2 | Staff, Admin | Trương Phú Hưng | In progress | 2
26 | Implement Video Tutorials and Product Comments Frontend | Build interfaces for: Product comments, Viewing video tutorials | Dashboard | Others | Iteration 2 | Staff, Admin, Doctor, Customer | Nguyễn Huỳnh Chấn Hưng | In progress | 2
27 | Write SRS document | Complete table in UC-E-1-1, UC-E-1-2, UC-E-1-3 |  |  | Iteration 3 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
28 | Write SRS document | Complete table in UC-E-2-1, UC-E-2-2, UC-E-2-3, UC-E-2-4 |  |  | Iteration 3 |  | Võ Chánh Huy | Backlog | 1
29 | Write SRS document | Complete table in UC-E-3-1, UC-E-3-2, UC-E-3-3, UC-E-3-4 |  |  | Iteration 3 |  | Võ Chánh Huy | Backlog | 1
30 | Write SRS document | Complete table in UC-E-4-1, UC-E-4-2, UC-E-4-3, UC-E-4-4, UC-E-4-5, UC-E-4-6, UC-E-4-7, UC-E-4-8 |  |  | Iteration 3 |  | Huỳnh Hoàng Huy | Backlog | 1
31 | Write SRS document | Complete table in UC-E-5-1, UC-E-5-2, UC-E-5-3, UC-E-5-4, UC-E-5-5 |  |  | Iteration 3 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
32 | Write SRS document | Complete table in UC-E-6-1, UC-E-6-2, UC-E-6-3 |  |  | Iteration 3 |  | Trương Phú Hưng | Backlog | 1
33 | Write SRS document | Complete table in UC-E-7-1, UC-E-7-2, UC-E-7-3, UC-E-7-4 |  |  | Iteration 3 |  | Trần Hữu Tín | Backlog | 1
34 | Download data as EXCEL | Download customer, product as EXCEL file |  |  | Iteration 3 |  | Võ Chánh Huy | Backlog | 3
35 | Auto generate customer ID | Auto generate customer ID, Staff ID, doctorID | Admin Dashboard | Others | Iteration 3 | Admin | Phan Thành Hưng | Backlog | 2
36 | Use `disable` instead of `readonly` in update pages | Use `disable` instead of `readonly` in update pages | Admin Dashboard | Others | Iteration 3 | Admin | Trần Hữu Tín | Backlog | 3
37 | Write SRS document | Complete table Business Rule & add BR to UC |  | Others | Iteration 3 |  | Trần Hữu Tín | Backlog | 1
38 | Complete Final Release Document |  |  | Others | Iteration 4 |  | Phan Thành Hưng | Backlog | 1
39 | Publish project on production |  |  | Others | Iteration 4 |  | Phan Thành Hưng | Backlog | 1
40 | System test document | List of all Test Cases implemented in the PawHouse | Admin Dashboard | Others | Iteration 4 | Admin | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
41 | Slide for UC-E-1-1, UC-E-1-2, UC-E-1-3, UC-E-2-1, UC-E-2-2 |  |  | Others | Iteration 4 |  | Huỳnh Hoàng Huy | Backlog | 2
42 | Slide for UC-E-2-3, UC-E-2-4, UC-E-3-1, UC-E-3-2, UC-E-3-3 |  |  | Others | Iteration 4 |  | Trần Hữu Tín | Backlog | 2
43 | Slide for UC-E-3-4, UC-E-4-1, UC-E--4-2, UC-E-4-3, UC-E-4-4 |  |  | Others | Iteration 4 |  | Huỳnh Hoàng Huy | Backlog | 2
44 | Slide for UC-E-4-5, UC-E-4-6, UC-E-4-7, UC-E-4-8, UC-E-5-1 |  |  | Others | Iteration 4 |  | Trương Phú Hưng | Backlog | 2
45 | Slide for UC-E-5-2, UC-E-5-3, UC-E-5-4, UC-E-5-5, UC-E-6-1 |  |  | Others | Iteration 4 |  | Huỳnh Hoàng Huy | Backlog | 2
46 | Slide for UC-E-6-2, UC-E-6-3, UC-E-7-1, UC-E-7-2, UC-E-7-3, UC-E-7-4 |  |  | Others | Iteration 4 |  | Huỳnh Hoàng Huy | Backlog | 2
47 | Slide for Document |  |  | Others | Iteration 4 |  | Phan Thành Hưng | Backlog | 1
49 | Record video |  |  | Others | Iteration 4 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 2

## Iteration1
Iteration 1
# | Title | Description | Assignee | Status | Priority | SRS | SDS | Note
1 | Upload SDS document to Google Docs | Upload SDS document to Google Docs | Huỳnh Hoàng Huy | Done | 1
2 | Upload Final Release document to Google Docs | Upload Final Release document to Google Docs | Phan Thành Hưng | Done | 1
3 | Upload SRS document to Google Docs | Upload SRS document to Google Docs | Nguyễn Huỳnh Chấn Hưng | Done | 1
4 | Design Database | Design and create Database | Trần Hữu Tín | Done | 1
5 | Upload Issues Report to Google Sheets | Upload Issues Report to Google Sheets | Phan Thành Hưng | Done | 2
6 | Setup Imgbot | Setup Imgbot | Huỳnh Hoàng Huy | Done | 2
7 | Setup CI | Setup auto build & release CI | Nguyễn Huỳnh Chấn Hưng | Done | 3
8 | Upload Project Tracking to Google Sheets | Upload Project Tracking to Google Sheets | Nguyễn Huỳnh Chấn Hưng | Done | 3
9 | Database: update SDS document | Add database design information in SDS document | Huỳnh Hoàng Huy | Done | 2
10 | Some errors in database | Some errors in the database design process | Phan Thành Hưng | Done | 2
11 | Write SRS - Draw the ERD model I.3 | Draw the ERD model and add Entities description | Trương Phú Hưng | Done | 1
12 | Write SRS - II.1 - Manage customer | Write detail function trigger, description and layout of Manage customer for SRS Document | Võ Chánh Huy | Done | 1
13 | Write SRS - II.2 - Manage pet | Write detail function trigger, description and layout of Manage pet for SRS Document | Võ Chánh Huy | Done | 1
14 | Write SRS - II.3 - Manage medicine | Write detail function trigger, description and layout of Manage medicine for SRS Document | Trương Phú Hưng | Done | 1
15 | Write SRS - II.4 - Manage service | Write detail function trigger, description and layout of Manage service for SRS Document | Huỳnh Hoàng Huy | Done | 1
16 | Write SRS - II.5 - Manage order | Write detail function trigger, description and layout of Manage order for SRS Document | Huỳnh Hoàng Huy | Done | 1
17 | Write SRS - II.6 - Manage product comment | Write detail function trigger, description and layout of Manage product comment for SRS Document | Huỳnh Hoàng Huy | Done | 2
18 | Write SRS - II.7 - Create account | Write detail function trigger, description and layout of Create account for SRS Document | Nguyễn Huỳnh Chấn Hưng | Done | 1
19 | Upload SRS document to Google Docs | Upload SRS document to Google Docs | Phan Thành Hưng | Done | 3
20 | Write all model classes | Write all model to store database from database | Trần Hữu Tín | Done | 1
21 | Write all DAO classes | Write all DAO classes to access data from database | Trần Hữu Tín | Done | 1

## Iteration2
Iteration 2
# | Title | Description | Screen / Function | Feature | Actor | Assignee | Status | Priority | SRS | SDS | Note
1 | Implement PawHouse for repository | Write PawHousefile and pawhouse-compose.yml |  |  |  | Trần Hữu Tín | In progress | 1
2 | Write code base UI | Write code base UI for project |  |  |  | Phan Thành Hưng | In progress | 1
3 | Write nav, sidenav, footer jsp | Write common jsp for reuse |  |  |  | Phan Thành Hưng | In progress | 1
4 | Write APIs for dashboard | Write APIs for dashboard | Dashboard | Others | Guest, Customer, Admin, Staff, Doctor | Huỳnh Hoàng Huy | In progress | 1
5 | Implment dashboard with charts | Implment dashboard with charts | Dashboard | Others | Guest, Customer, Admin, Staff, Doctor | Huỳnh Hoàng Huy | In progress | 2
6 | Implement Authentication and Profile Management Backend | Develop APIs for: Login (UC-E-7-2), Register (UC-E-7-1), Forget Password, Logout (UC-E-7-3), View Profile, Update Profile, Change Password | Login | Others | Guest, Customer, Admin, Staff, Doctor | Trương Phú Hưng | In progress | 1
7 | Implement Authentication and Profile Management Frontend | Build interfaces for: Login, Register, Forget Password, Profile View, Profile Update | Login | Others | Guest, Customer, Admin, Staff, Doctor | Trương Phú Hưng | In progress | 1
8 | Implement Product Management Backend | Develop APIs for: View Product (UC-E-3-1), Create New Product (UC-E-3-2), Edit Product (UC-E-3-4), Delete Product | Manage Product | Product Management | Staff, Admin, Doctor | Nguyễn Huỳnh Chấn Hưng | In progress | 1
9 | Implement Product Management Frontend | Build product display pages, Create product management interfaces (add, edit, delete) | Manage Product | Product Management | Staff, Admin, Doctor | Võ Chánh Huy | In progress | 1
10 | Implement Shopping Cart and Payment Backend | Develop APIs for: Edit Product in Cart, View Cart, Delete Product in Cart, Make Payment by Cash, Make Payment by Card | Manage Product | Product Management | Customer | Võ Chánh Huy | In progress | 1
11 | Implement Shopping Cart and Payment Frontend | Build product display pages, create shopping cart and payment pages | Dashboard | Others | Customer | Phan Thành Hưng | In progress | 1
12 | Implement Service Management Backend | Develop APIs for: View All Services (UC-E-4-1), Add New Service (UC-E-4-2), View Service Details (UC-E-4-3), Update Service (UC-E-4-4), Booking Service Appointment (UC-E-4-5), View Appointment Details (UC-E-4-6), Update Appointment (UC-E-4-7), Cancel Appointment (UC-E-4-8) | Manage Services | Service Management | Staff, Admin, Doctor, Customer | Huỳnh Hoàng Huy | In progress | 2
13 | Implement Service Management Frontend | Build service listing and detail pages, Create appointment management interfaces | Manage Services | Service Management | Staff, Admin, Doctor, Customer | Huỳnh Hoàng Huy | In progress | 2
14 | Implement Pet and Health Management Backend | Develop APIs for: View Pet List (UC-E-2-1), Create New Pet (UC-E-2-2), Edit Pet (UC-E-2-4), Delete Pet, Health Tracking, Drug Management, Disease Management, Disease Update | Manage Pet | Pet Management | Staff, Admin, Doctor, Customer | Trần Hữu Tín | In progress | 2
15 | Implement Pet and Health Management Frontend | Build interfaces for: Pet management, Health tracking and disease management | Dashboard | Others | Doctor, Customer | Trần Hữu Tín | In progress | 2
16 | Implement Staff and Doctor Management Backend | Develop APIs for: View Doctor List, Manage Doctor, Create New Account, Edit Account, Delete Account, View Staff Logs | Admin Dashboard | Customer Management | Admin | Trần Hữu Tín | In progress | 2
17 | Implement Staff and Doctor Management Frontend | Build interfaces for staff and doctor management | Manage Services | Service Management | Staff, Admin | Phan Thành Hưng | In progress | 2
18 | Implement Reporting and Insights Backend | Develop APIs for: View Service History; View Order Products; View Reports by Day, Month, and Year | Dashboard | Others | Staff, Doctor, Customer | Phan Thành Hưng | In progress | 3
19 | Implement Reporting and Insights Frontend | Create report and transaction history interfaces | Dashboard | Others | Staff, Doctor, Customer | Trương Phú Hưng | In progress | 3
20 | Implement Video Tutorials and Product Comments Backend | Develop APIs for: View Product Comments (UC-E-6-1), Add Comment (UC-E-6-1), Update Comment (UC-E-6-3), Delete Comment (UC-E-6-2), View Video Tutorials | Dashboard | Others | Staff, Admin | Trương Phú Hưng | In progress | 2
21 | Implement Video Tutorials and Product Comments Frontend | Build interfaces for: Product comments, Viewing video tutorials | Dashboard | Others | Staff, Admin, Doctor, Customer | Nguyễn Huỳnh Chấn Hưng | In progress | 2

## Iteration3
Iteration 3
# | Title | Description | Actor | Assignee | Status | Priority | SRS | SDS | Note
1 | Write SRS document | Complete table in UC-E-1-1, UC-E-1-2, UC-E-1-3 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
2 | Write SRS document | Complete table in UC-E-2-1, UC-E-2-2, UC-E-2-3, UC-E-2-4 |  | Võ Chánh Huy | Backlog | 1
3 | Write SRS document | Complete table in UC-E-3-1, UC-E-3-2, UC-E-3-3, UC-E-3-4 |  | Võ Chánh Huy | Backlog | 1
4 | Write SRS document | Complete table in UC-E-4-1, UC-E-4-2, UC-E-4-3, UC-E-4-4, UC-E-4-5, UC-E-4-6, UC-E-4-7, UC-E-4-8 |  | Huỳnh Hoàng Huy | Backlog | 1
5 | Write SRS document | Complete table in UC-E-5-1, UC-E-5-2, UC-E-5-3, UC-E-5-4, UC-E-5-5 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
6 | Write SRS document | Complete table in UC-E-6-1, UC-E-6-2, UC-E-6-3 |  | Trương Phú Hưng | Backlog | 1
7 | Write SRS document | Complete table in UC-E-7-1, UC-E-7-2, UC-E-7-3, UC-E-7-4 |  | Trần Hữu Tín | Backlog | 1
8 | Download data as EXCEL | Download customer, product as EXCEL file |  | Võ Chánh Huy | Backlog | 3
9 | Auto generate customer ID | Auto generate customer ID, Staff ID, doctorID | Admin | Phan Thành Hưng | Backlog | 2
10 | Use `disable` instead of `readonly` in update pages | Use `disable` instead of `readonly` in update pages | Admin | Trần Hữu Tín | Backlog | 3
11 | Write SRS document | Complete table Business Rule & add BR to UC |  | Trần Hữu Tín | Backlog | 1

## Iteration4
Iteration 4
# | Title | Description | Actor | Assignee | Status | Priority | SRS | SDS | Note
1 | Complete Final Release Document |  |  | Phan Thành Hưng | Backlog | 1
2 | Publish project on production |  |  | Phan Thành Hưng | Backlog | 1
3 | System test document | List of all Test Cases implemented in the PawHouse | Admin | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
4 | Slide for UC-E-1-1, UC-E-1-2, UC-E-1-3, UC-E-2-1, UC-E-2-2 |  |  | Huỳnh Hoàng Huy | Backlog | 2
5 | Slide for UC-E-2-3, UC-E-2-4, UC-E-3-1, UC-E-3-2, UC-E-3-3 |  |  | Trần Hữu Tín | Backlog | 2
6 | Slide for UC-E-3-4, UC-E-4-1, UC-E--4-2, UC-E-4-3, UC-E-4-4 |  |  | Huỳnh Hoàng Huy | Backlog | 2
7 | Slide for UC-E-4-5, UC-E-4-6, UC-E-4-7, UC-E-4-8, UC-E-5-1 |  |  | Trương Phú Hưng | Backlog | 2
8 | Slide for UC-E-5-2, UC-E-5-3, UC-E-5-4, UC-E-5-5, UC-E-6-1 |  |  | Huỳnh Hoàng Huy | Backlog | 2
9 | Slide for UC-E-6-2, UC-E-6-3, UC-E-7-1, UC-E-7-2, UC-E-7-3, UC-E-7-4 |  |  | Huỳnh Hoàng Huy | Backlog | 2
10 | Slide for Document |  |  | Phan Thành Hưng | Backlog | 1
11 | Record video | Edit video User manual |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 2