## Infomation
SWP391 - Group 1
I. Members |  |  | II. Project's information
# | Full name | Student ID | # | Field | Value
1 | Phan Thành Hưng | CE180265 | 1 | Project Name | PawHouse
2 | Trần Hữu Tín | CE180262 | 2 | Repository | GitHub
3 | Nguyễn Huỳnh Chấn Hưng | CE180150 | 3 | RDS Document
4 | Trương Phú Hưng | CE180618 | 4 | SDS Document
5 | Huỳnh Hoàng Huy | CE181847 | 5 | Issues Report
6 | Võ Chánh Huy | CE181002 | 6 | Final Release Document

## Project
THE APPLICATION DEVELOPMENT PROJECT TOPIC PRODUCT BACKLOG
# | Title | Description | Screen / Function | Feature | Iteration | GitHub Issue | Assignee | Status | Priority | SRS | SDS | Note
1 | Write all model classes | Write all model to store database from database |  |  | Iteration 1 |  | Phan Thành Hưng | Backlog | 1
2 | Write all DAO classes | Write all DAO classes to access data from database |  |  | Iteration 1 |  | Phan Thành Hưng | Backlog | 2
3 | Write code base | Write code base for project |  |  | Iteration 2 |  | Trần Hữu Tín | Backlog | 1
4 | Implement Pet for repository | Write Petfile and Pet-compose.yml |  |  | Iteration 2 |  | Huỳnh Hoàng Huy | Backlog | 1
5 | Write nav, sidenav, footer jsp | Write common jsp for reuse |  |  | Iteration 2 |  | Võ Chánh Huy | Backlog | 1
6 | Implement login & forgot password pages | Implement login & forgot password pages | Login | Others | Iteration 2 |  | Võ Chánh Huy | Backlog | 1
7 | Implment customer page | Implment customer table page | List all customers | Customer Management | Iteration 2 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
8 | Implment customer detail page | Implment customer detail page | Customer detail | Customer Management | Iteration 2 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
9 | Implment add customer page | Implment add customer page | Add a customer | Customer Management | Iteration 2 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
10 | Implment product page | Implment product page | List all products | Product Management | Iteration 2 |  | Võ Chánh Huy | Backlog | 2
11 | Implment order page | Implment order page | List all orders | Order Management | Iteration 2 |  | Võ Chánh Huy | Backlog | 2
12 | Design UI | Design UI |  |  | Iteration 2 |  | Trần Hữu Tín | Backlog | 1
14 | Implment order detail | Implment order detail | Order detail | Order Management | Iteration 2 |  | Trần Hữu Tín | Backlog | 2
15 | Implment product detail | Implment product detail | Product detail | Product Management | Iteration 2 |  | Phan Thành Hưng | Backlog | 2
16 | Write APIs for dashboard | Write APIs for dashboard | Dashboard | Others | Iteration 2 |  | Trương Phú Hưng | Backlog | 1
17 | Implment dashboard with charts | Implment dashboard with charts | Dashboard | Others | Iteration 2 |  | Trương Phú Hưng | Backlog | 2
18 | Implment add product page | Implment add product page | Add a product | Product Management | Iteration 3 |  | Trương Phú Hưng | Backlog | 1
19 | Implment add order page | Implment add order page | Add a order | Order Management | Iteration 3 |  | Trương Phú Hưng | Backlog | 1
20 | Implment update customer page | Implment update customer page (name, address) | Edit a customer | Customer Management | Iteration 3 |  | Trần Hữu Tín | Backlog | 1
21 | Implment update product page | Implment update product page (name, price, image, note) | Edit a product | Product Management | Iteration 3 |  | Trần Hữu Tín | Backlog | 1
22 | Implment update order page | Implment update order page (status if status not 'DONE' or 'CANCELLED') | Edit a order | Order Management | Iteration 3 |  | Huỳnh Hoàng Huy | Backlog | 1
23 | Implment paging for product page | Implment paging for product page | List all products | Product Management | Iteration 3 |  | Phan Thành Hưng | Backlog | 2
24 | Implment paging for customer page | Implment paging for customer page | List all customers | Customer Management | Iteration 3 |  | Trương Phú Hưng | Backlog | 1
25 | Implment paging for order page | Implment paging for order page | List all orders | Order Management | Iteration 3 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 2
26 | Write SRS document | Complete table in UC-E-1-1, UC-E-1-2, UC-E-1-3, UC-E-1-4 |  | Others | Iteration 3 |  | Trương Phú Hưng | Backlog | 1
27 | Write SRS document | Complete table in UC-E-2-1, UC-E-2-2, UC-E-2-3, UC-E-2-4 |  | Others | Iteration 3 |  | Võ Chánh Huy | Backlog | 1
28 | Write SRS document | Complete table in UC-E-3-1, UC-E-3-3, UC-E-3-4 |  | Others | Iteration 3 |  | Huỳnh Hoàng Huy | Backlog | 1
29 | Write SRS document | Complete table in UC-E-4-1, UC-E-4-2, UC-E-4-3 |  | Others | Iteration 3 |  | Huỳnh Hoàng Huy | Backlog | 1
30 | Download data as EXCEL | Download customer, product as EXCEL file |  | Others | Iteration 3 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
31 | Add status order in list order | Add status order in list order PET | List all orders | Order Management | Iteration 3 |  | Phan Thành Hưng | Backlog | 1
32 | Update paging for order page | When change page number to letter or negative number, it will redirect to 404 error page instead of returning to page 1 | List all orders | Order Management | Iteration 3 |  | Phan Thành Hưng | Backlog | 1
33 | Auto generate customer ID | Auto generate customer ID, Staff ID, doctorID |  |  | Iteration 3 |  | Phan Thành Hưng | Backlog | 2
34 | Use `disable` instead of `readonly` in update pages | Use `disable` instead of `readonly` in update pages |  |  | Iteration 3 |  | Phan Thành Hưng | Backlog | 1
35 | Write SRS document | Complete table Business Rule & add BR to UC |  | Others | Iteration 3 |  | Huỳnh Hoàng Huy | Backlog | 2
36 | Complete Final Release Document |  |  |  | Iteration 4 |  | Huỳnh Hoàng Huy | Backlog | 1
37 | Publish project on production |  |  |  | Iteration 4 |  | Huỳnh Hoàng Huy | Backlog | 2
38 | Record video |  |  |  | Iteration 4 |  | Trần Hữu Tín | Backlog | 3
39 | System test document | List of all Test Cases implemented in the PawHouse |  |  | Iteration 4 |  | Trần Hữu Tín | Backlog | 1
40 | Slide for UC-E-1-1, UC-E-1-2, UC-E-1-3 |  |  |  | Iteration 4 |  | Trần Hữu Tín | Backlog | 1
41 | Slide for UC-E-1-4, UC-E-2-1, UC-E-2-2 |  |  |  | Iteration 4 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
42 | Slide for UC-E-2-3, UC-E-2-4, UC-E-3-1 |  |  |  | Iteration 4 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 1
43 | Slide for UC-E-3-2, UC-E-3-3, UC-E-3-4 |  |  |  | Iteration 4 |  | Nguyễn Huỳnh Chấn Hưng | Backlog | 2
44 | Slide for UC-E-4-1, UC-E-4-2, UC-E-4-3 |  |  |  | Iteration 4 |  | Phan Thành Hưng | Backlog | 1
45 | Slide for Document |  |  |  | Iteration 4 |  | Phan Thành Hưng | Backlog | 3
46